## Single
Project Management (Single Time Estimate) | [12 empty] | Project Completion Time = |  |  |  |  | 26
| Task Description | Time |  |  | Pred 1 | Pred 2 | Pred 3 | Pred 4 | Pred 5 |  | Time |  | Early Start | Early Finish | Late Start | Late Finish | Slack | Critical Path | Task
A | Prepare arch drawings | 5 | [8 empty] | 5 |  | 0 | 5 | 0 | 5 | 0 | YES | A | 0
B | Identify potential tenants | 6 | [8 empty] | 6 |  | 0 | 6 | 6 | 12 | 6 |  |  | 0
C | Develop prospectus | 4 |  |  | A | [5 empty] | 4 |  | 5 | 9 | 8 | 12 | 3 |  |  | 0
D | Select contractor | 3 |  |  | A | [5 empty] | 3 |  | 5 | 8 | 7 | 10 | 2 |  |  | 0
E | Prepare permits | 1 |  |  | A | [5 empty] | 1 |  | 5 | 6 | 5 | 6 | 0 | YES | E | 0
F | Obtain approval for permit | 4 |  |  | E | [5 empty] | 4 |  | 6 | 10 | 6 | 10 | 0 | YES | F | 0
G | Perform construction | 14 |  |  | D | F |  |  |  |  | 14 |  | 10 | 24 | 10 | 24 | 0 | YES | G | 0
H | Finalize contracts with tenants | 12 |  |  | B | C |  |  |  |  | 12 |  | 9 | 21 | 12 | 24 | 3 |  |  | 0
I | Tenants move in | 2 |  |  | G | H |  |  |  |  | 2 |  | 24 | 26 | 24 | 26 | 0 | YES | I | 0
J | [10 empty] | 0 |  | 0 | 0 | 26 | 26 | 26 |  |  | 0
K | [10 empty] | 0 |  | 0 | 0 | 26 | 26 | 26 |  |  | 0
L | [10 empty] | 0 |  | 0 | 0 | 26 | 26 | 26 |  |  | 0
M | [10 empty] | 0 |  | 0 | 0 | 26 | 26 | 26 |  |  | 0
N | [10 empty] | 0 |  | 0 | 0 | 26 | 26 | 26 |  |  | 0
O | [10 empty] | 0 |  | 0 | 0 | 26 | 26 | 26 |  |  | 0
P | [10 empty] | 0 |  | 0 | 0 | 26 | 26 | 26 |  |  | 0
Q | [10 empty] | 0 |  | 0 | 0 | 26 | 26 | 26 |  |  | 0
R | [10 empty] | 0 |  | 0 | 0 | 26 | 26 | 26 |  |  | 0
S | [10 empty] | 0 |  | 0 | 0 | 26 | 26 | 26 |  |  | 0
T | [10 empty] | 0 |  | 0 | 0 | 26 | 26 | 26 |  |  | 0
U | [10 empty] | 0 |  | 0 | 0 | 26 | 26 | 26 |  |  | 0
V | [10 empty] | 0 |  | 0 | 0 | 26 | 26 | 26 |  |  | 0
W | [10 empty] | 0 |  | 0 | 0 | 26 | 26 | 26 |  |  | 0
X | [10 empty] | 0 |  | 0 | 0 | 26 | 26 | 26 |  |  | 0
Y | [10 empty] | 0 |  | 0 | 0 | 26 | 26 | 26 |  |  | 0
Z | [10 empty] | 0 |  | 0 | 0 | 26 | 26 | 26 |  |  | 0
Early start computations
A |  |  | 0 | 0 | 0 | 0 | 0
B |  |  | 0 | 0 | 0 | 0 | 0
C |  |  | 5 | 0 | 0 | 0 | 0
D |  |  | 5 | 0 | 0 | 0 | 0
E |  |  | 5 | 0 | 0 | 0 | 0
F |  |  | 6 | 0 | 0 | 0 | 0
G |  |  | 8 | 10 | 0 | 0 | 0
H |  |  | 6 | 9 | 0 | 0 | 0
I |  |  | 24 | 21 | 0 | 0 | 0
J |  |  | 0 | 0 | 0 | 0 | 0
K |  |  | 0 | 0 | 0 | 0 | 0
L |  |  | 0 | 0 | 0 | 0 | 0
M |  |  | 0 | 0 | 0 | 0 | 0
N |  |  | 0 | 0 | 0 | 0 | 0
O |  |  | 0 | 0 | 0 | 0 | 0
P |  |  | 0 | 0 | 0 | 0 | 0
Q |  |  | 0 | 0 | 0 | 0 | 0
R |  |  | 0 | 0 | 0 | 0 | 0
S |  |  | 0 | 0 | 0 | 0 | 0
T |  |  | 0 | 0 | 0 | 0 | 0
U |  |  | 0 | 0 | 0 | 0 | 0
V |  |  | 0 | 0 | 0 | 0 | 0
W |  |  | 0 | 0 | 0 | 0 | 0
X |  |  | 0 | 0 | 0 | 0 | 0
Y |  |  | 0 | 0 | 0 | 0 | 0
Z |  |  | 0 | 0 | 0 | 0 | 0
Late finish computations
|  | A | B | C | D | E | F | G | H | I | J | K | L | M | N | O | P | Q | R | S | T | U | V | W | X | Y | Z
A |  | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26
B |  | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26
C |  | 8 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26
D |  | 7 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26
E |  | 5 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26
F |  | 26 | 26 | 26 | 26 | 6 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26
G |  | 26 | 26 | 26 | 10 | 26 | 10 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26
H |  | 26 | 12 | 12 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26
I |  | 26 | 26 | 26 | 26 | 26 | 26 | 24 | 24 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26
J |  | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26
K |  | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26
L |  | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26
M |  | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26
N |  | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26
O |  | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26
P |  | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26
Q |  | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26
R |  | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26
S |  | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26
T |  | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26
U |  | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26
V |  | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26
W |  | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26
X |  | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26
Y |  | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26
Z |  | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26
|  | 5 | 12 | 12 | 10 | 6 | 10 | 24 | 24 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26 | 26
Graph
A | 0 | A: 5
B | 0 | A: 6
C | 5 | A: 4
D | 5 | A: 3
E | 5 | bar: A
F | 6 | A: 4
G | 10 | A: 14
H | 9 | A: 12
I | 24 | A: 2
J | 0 | A: 0
K | 0 | A: 0
L | 0 | A: 0
M | 0 | A: 0
N | 0 | A: 0
O | 0 | A: 0
P | 0 | A: 0
Q | 0 | A: 0
R | 0 | A: 0
S | 0 | A: 0
T | 0 | A: 0
U | 0 | A: 0
V | 0 | A: 0
W | 0 | A: 0
X | 0 | A: 0
Y | 0 | A: 0
Z | 0 | A: 0

## Triple
Project Management (Triple Time Estimate) | [10 empty] | Project Completion Time = |  |  |  | 15
[11 empty] | StdDev of Completion Time = |  |  |  | 1.7594
| Task Description | Optimistic | Likely | Pessimistic | Pred 1 | Pred 2 | Pred 3 | Pred 4 | Pred 5 |  | Time | Std dev | Early Start | Early Finish | Late Start | Late Finish | Slack | Critical Path | Task
A | Build components | 1 | 2 | 3 | [6 empty] | 2 | 0.33 | 0 | 2 | 0 | 2 | 0 | YES | A | 0.1089
B | Modify roof and floor | 2 | 3 | 4 | [6 empty] | 3 | 0.33 | 0 | 3 | 1 | 4 | 1 |  |  | 0
C | Collection stack | 1 | 2 | 3 | A | [5 empty] | 2 | 0.33 | 2 | 4 | 2 | 4 | 0 | YES | C | 0.1089
D | Concrete / frame | 2 | 4 | 6 | B | [5 empty] | 4 | 0.67 | 3 | 7 | 4 | 8 | 1 |  |  | 0
E | High-temp burner | 1 | 4 | 7 | C | [5 empty] | 4 | 1 | 4 | 8 | 4 | 8 | 0 | YES | E | 1
F | Install control system | 1 | 2 | 9 | C | [5 empty] | 3 | 1.33 | 4 | 7 | 10 | 13 | 6 |  |  | 0
G | Install air pollution device | 3 | 4 | 11 | D | E |  |  |  |  | 5 | 1.33 | 8 | 13 | 8 | 13 | 0 | YES | G | 1.7689
H | Inspect and test | 1 | 2 | 3 | F | G |  |  |  |  | 2 | 0.33 | 13 | 15 | 13 | 15 | 0 | YES | H | 0.1089
I | [10 empty] | 0 | 0 | 0 | 0 | 15 | 15 | 15 |  |  | 0
J | [10 empty] | 0 | 0 | 0 | 0 | 15 | 15 | 15 |  |  | 0
K | [10 empty] | 0 | 0 | 0 | 0 | 15 | 15 | 15 |  |  | 0
L | [10 empty] | 0 | 0 | 0 | 0 | 15 | 15 | 15 |  |  | 0
M | [10 empty] | 0 | 0 | 0 | 0 | 15 | 15 | 15 |  |  | 0
N | [10 empty] | 0 | 0 | 0 | 0 | 15 | 15 | 15 |  |  | 0
O | [10 empty] | 0 | 0 | 0 | 0 | 15 | 15 | 15 |  |  | 0
P | [10 empty] | 0 | 0 | 0 | 0 | 15 | 15 | 15 |  |  | 0
Q | [10 empty] | 0 | 0 | 0 | 0 | 15 | 15 | 15 |  |  | 0
R | [10 empty] | 0 | 0 | 0 | 0 | 15 | 15 | 15 |  |  | 0
S | [10 empty] | 0 | 0 | 0 | 0 | 15 | 15 | 15 |  |  | 0
T | [10 empty] | 0 | 0 | 0 | 0 | 15 | 15 | 15 |  |  | 0
U | [10 empty] | 0 | 0 | 0 | 0 | 15 | 15 | 15 |  |  | 0
V | [10 empty] | 0 | 0 | 0 | 0 | 15 | 15 | 15 |  |  | 0
W | [10 empty] | 0 | 0 | 0 | 0 | 15 | 15 | 15 |  |  | 0
X | [10 empty] | 0 | 0 | 0 | 0 | 15 | 15 | 15 |  |  | 0
Y | [10 empty] | 0 | 0 | 0 | 0 | 15 | 15 | 15 |  |  | 0
Z | [10 empty] | 0 | 0 | 0 | 0 | 15 | 15 | 15 |  |  | 0
Probability that completion is less than |  |  |  | 13 | ==> | 12.78%
Probability that completion is greater than |  |  |  | 18 | ==> | 4.409% | [13 empty] | 1.7594
Early start computations
A |  |  | 0 | 0 | 0 | 0 | 0
B |  |  | 0 | 0 | 0 | 0 | 0
C |  |  | 2 | 0 | 0 | 0 | 0
D |  |  | 3 | 0 | 0 | 0 | 0
E |  |  | 4 | 0 | 0 | 0 | 0
F |  |  | 4 | 0 | 0 | 0 | 0
G |  |  | 7 | 8 | 0 | 0 | 0
H |  |  | 7 | 13 | 0 | 0 | 0
I |  |  | 0 | 0 | 0 | 0 | 0
J |  |  | 0 | 0 | 0 | 0 | 0
K |  |  | 0 | 0 | 0 | 0 | 0
L |  |  | 0 | 0 | 0 | 0 | 0
M |  |  | 0 | 0 | 0 | 0 | 0
N |  |  | 0 | 0 | 0 | 0 | 0
O |  |  | 0 | 0 | 0 | 0 | 0
P |  |  | 0 | 0 | 0 | 0 | 0
Q |  |  | 0 | 0 | 0 | 0 | 0
R |  |  | 0 | 0 | 0 | 0 | 0
S |  |  | 0 | 0 | 0 | 0 | 0
T |  |  | 0 | 0 | 0 | 0 | 0
U |  |  | 0 | 0 | 0 | 0 | 0
V |  |  | 0 | 0 | 0 | 0 | 0
W |  |  | 0 | 0 | 0 | 0 | 0
X |  |  | 0 | 0 | 0 | 0 | 0
Y |  |  | 0 | 0 | 0 | 0 | 0
Z |  |  | 0 | 0 | 0 | 0 | 0
Late finish computations
|  | A | B | C | D | E | F | G | H | I | J | K | L | M | N | O | P | Q | R | S | T | U | V | W | X | Y | Z
A |  | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
B |  | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
C |  | 2 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
D |  | 15 | 4 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
E |  | 15 | 15 | 4 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
F |  | 15 | 15 | 10 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
G |  | 15 | 15 | 15 | 8 | 8 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
H |  | 15 | 15 | 15 | 15 | 15 | 13 | 13 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
I |  | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
J |  | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
K |  | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
L |  | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
M |  | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
N |  | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
O |  | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
P |  | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
Q |  | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
R |  | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
S |  | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
T |  | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
U |  | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
V |  | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
W |  | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
X |  | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
Y |  | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
Z |  | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
|  | 2 | 4 | 4 | 8 | 8 | 13 | 13 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
Graph
A |  | A: 0; B: 2
B |  | A: 0; B: 3
C |  | A: 2; B: 2
D |  | A: 3; B: 4
E |  | A: 4; B: 4
F |  | A: 4; B: 3
G |  | A: 8; B: 5
H |  | A: 13; B: 2
I |  | A: 0; B: 0
J |  | A: 0; B: 0
K |  | A: 0; B: 0
L |  | A: 0; B: 0
M |  | A: 0; B: 0
N |  | A: 0; B: 0
O |  | A: 0; B: 0
P |  | A: 0; B: 0
Q |  | A: 0; B: 0
R |  | A: 0; B: 0
S |  | A: 0; B: 0
T |  | A: 0; B: 0
U |  | A: 0; B: 0
V |  | A: 0; B: 0
W |  | A: 0; B: 0
X |  | A: 0; B: 0
Y |  | A: 0; B: 0
Z |  | A: 0; B: 0
Note on E32: Input the value for which you want to compute the probability of being less than.
Note on E33: Input the value for which you want to compute the probability of being greater than.